## planning
Draft WASH Sector Workplan 2024
Objectives / main activities | Lead | Importance | Timing
Develop long-term strategy and cost efficient of the WASH response
Operationalisation of the FSM strategy | WASH co + Jafar + OXFAM | 4 | 1st Semester
Develop water strategy (long-term) | WASH Sector + Core team | 5 | 2 & 3 trimester
Plan/support discussions to reorganise AFA per camps | WASH Co + senior IOM-UNHCR-UNICEF + ISCG | 5 | Through the year
Apply Rationzalisation principles | WASH Co, partners | 5 | Through the year
Better integration of cost efficiency and sustainability in the operationsalisation of the response | WASH Co, partners, lead TCG | 4 | Through the year
Build capacities of partners
Organise regular webinars | Sector + partners | 3 | Through the year
Exchange of experience between actors at field level | Sector + partners + CFP | 4 | Through the year
Support key partners (new actors, camps with low performances) directly on the field | Sector + partners + CFP | 3 | Through the year
Training on emergency response | Sector + partner | 3 | second trimester
Organise WASH training on specific issues identified as gap (IM training, operation of water-network, chlorination…) | Sector team | 2 | Through the year
Reinforce prepardness and reponse capacity
Capacity building (outbreak/fire/cyclone) | WASH sector, CFP | 3 | Through the year
Assess WASH items prepositionned for emergency response | IM | 3
Develop multi-sectorial plan for new influx | ISCG | 3
Collaborate with fire response agencies | WASH sector, CFP | 3
Strengh monitoring to identify priorities and gaps
Simplify 4W tool (consider a simple form for HC) | IM | 3 | From January
Develop Solid Waste monitoring dasboard | Tanvir + jafar | 3 | 1st semester
Establish Water-network monitoring and advocacy | MSF + jafar + tanvir | 3 | 1st semester
Support HC sub coordination platform to develop monitoring tool
Kobo update on JART | tanvir + PHP |  | Mostly 1st trimester
Include graphs with the evolution over time of key indicators (in existing dashboard or in next dashbaord) | Tanvir | 4 | mid-2024
Monitor & Review key indicators of Overview tool | Tanvir | 4 | through the year
Follow-up on corrective actions from monitoring tools | CFP + Jafar + liaison | 3 | through the year
Make sure of efficient & harmonised HH monitoring tools aligned to JRP and "overview tool" | AFA / IM / WASH Co | 3 | 2nd trimester
Continue management and monitoring of key WASH sector IM tools | IM | 4 | through the year
Strenght collaboration with ISCG keys sectors
Report on JRP progress and develop JRP 2025 | WASH Co | 3 | through the year / last trimester
WASH's interests are represented within ISCG | WASH Co | 3 | through the year
Health - Outbreak preparedness and response | PHP Specialist, MSF | 3 | 1st semester
SCCCM - collaboration integrated Shelter-WASH | WASH Co + jafar | 3 | through the year
Livelihood - collaboration on MHM
Develop SOP on WASH in institution | PHP Specialist | 3 | 2nd trimester
Inclusion: Gender, resilience, environment, AAP | PHP Specialist | 3 | through the year
Strenght communication and partnership with authorities
Provide regular WASH updates to DPHE / RRRC | Liaison, WSH Co | 3 | through the year
Built-up working relationship with RRRC to support advocacy | Liaison, WSH Co | 4 | through the year
Increase collaboration with DPHE Dhaka and its partners (WB, ADB) | WASH Co / AFAs | 4 | through the year
Develop communication video/"pager" on achievements and challenges | WASH Co + Tonmoy | 3 | 1st semester 2024
Advocate to authorities on 1) landfill; 2) Community engagement; 3) Privatisation & policy | Liaison, WSH Co |  | 1st semester 2024
Advocate to main donors on gaps and priorities following "funding gaps analysis" | WASH Co + Tonmoy | 4 | February + July
Reinforce field coordination
Support WASH camps focal point system | Jafar + liaison | 4 | throught the year
Support partners at field level | WASH Co | 4 | throught the year
Support Upuzila coordination (ISCG, host community and camps) | Jafar | 3 | throught the year
Focus on key technical issues
Follow-up on MHM kits harmonisation | PHP lead + AFA | 4 | through the year
Strengh HP + CHW collaboration | PHP lead + AFA | 3
harmonisation ToR on user group | PHP lead | 3
Assess impacts and solution for residual waste and recycling | External expertise | 4
Child hygiene and well-being (study) | WASH Co, PHP | 3
Assess Waste generation at HH and shop level | SWM + WASH technical | 2
Study settled solid sludge | oxfam + jafar | 3
Develop WASH catalogue (assess possibility) | sector + partner (UNICEF?) | 2
ToR to clarify WASH responsabilities in the institutions in camps | WASH sector team | 3
Integrate better climate change into WASH resilient program | WASH sector team | 3