## Sheet1
1. Gender equality included in analysis, planning and design
# | Gender equality results & performance tracking | Performance indicator | Actions | Timeframe |  | Responsible | Status/Update |  |  | Remarks
|  |  |  | 2025 | 2026 |  |  | 25 | 26
1.1 | Result: Gender analysis of key gender issues is available across the different sectors of the Rohingya Refugee Response (RRR), covering analysis of key gender issues and Sex & Age Disaggregated Data (SADD). PT: Extent to which gender data and analysis relevant to the RRR is available. | 1.1.1 At least one joint gender analysis produced in relation to the inter-sectoral response and/or the JRP per year. | 1.1.1.1 Establishment of a Gender Data Task Force (TF) under the GiHA WG. | Q1-Q4 | Q1-Q4 | GiHA Coordinator | Aug '24: Proposed; yet to be initiated. |  |  | Status/Update:Nomination of Gender Data Task force members is done in March 2025
|  |  | 1.1.1.2 Conduct research on foundational issues underpinning gender inequalities. | Q2-Q4 | TBC | GiHA Coordinator, Gender Data TF |  |  |  | Gender analysis of foundational issues identified as priority by GiHA WG in 2023 Consultation WS. (Previous equivalent analysis is the 'Four Years On'-report). In Q3 of 2025, new research plan would be initiated.
|  | 1.1.2 ISNA is based on solid gender analysis and sex and age disaggregated data, which identifies gender inequalities that lead to different power, vulnerabilities, capacities, voice and participation of women, girls, men and boys. | 1.1.2.1. Review & provide gender specific inputs for incorporation in the ISNA survey questionnaire | Q2-Q3 | TBC | GiHA Coordinator Gender Data TF | Jul '25: ISNA questionnaire reviewed; indicators on gender disparities; feedback provided on SADD (UN Women) |  |  | Draft of GiHA indicators for ISNA 2025 has been drafted and will be shared with GD TF for review
|  |  | 1.1.2.2 Preparation of gender analytical report/brief based on ISNA data | Q4 | Q1 | GiHA Coordinator, Gender Data TF | Aug '25: ISNA data yet to be generated.
|  | 1.1.3 Sectors and sector assessments integrate gender analysis and SADD. | 1.1.3.1 Review of SWG/SS quarterly briefs to support gender analysis and capture key trends across response. | Ongoing | Ongoing | SWG/SS members of the GiHA WG | Aug '24: Initiated. |  |  | Need to strengthen role of GiHA WG members representing different sectors, including to ensure discussion.
1.2 | Result: Gender equality priorities included in the Joint Response Plan. PT: Extent to which 2-track gender mainstreaming for GEEWG are reflected in the JRP and sector plans (integration of gender considerations and analysis and actions dedicated to GEEWG) | 1.2.1 Gender analysis informs the development of the JRP. Develop a gender mainstreaming guideline for sectors and sub-sectors based on the study findings on gender equality priorities. | 1.2.1.1 Prepare a multi-sector gender & diversity analysis with the engagement of SWG/SS coordinators, building on quarterly SWG/SS reports. Set gender equality priorities for sectors and sub-sectors according the the GiHA studies and sector OPs and develop a guideline for twin track approach. (merging the 2 actions here or merging 1.2.1 and 1.2.2 as basically the tipsheets are the sector specific guidelines) | Q3-Q4 | TBC | GiHA Coordinator, Gender Data TF | Aug '25: Gender analysis of JRP indicators & objectives undertaken, in support of analysis.
|  |  | 1.2.1.2 Meeting of the Gender Data TF and SWG/SS Coordinators to identify clear sector-specific gender & inclusion priorities to include in OPs. | Q3-Q4 | TBC | GiHA Coordinator, Gender Data TF
|  | 1.2.2 Sectors and Sub-Sectors pursue a twin-track approach to gender mainstreaming, based on guidance. | 1.2.2.1 Develop & disseminate Gender Tipsheets (updating existing ones, developing new ones) to inform JRP project appeals. | Q2-Q4 | In advance of JRP | GiHA Coordinator, GiHA WG | Aug'24: WS conducted 30 Apr. Drafts developed & in need of review & finalization.
|  |  | 1.2.2.2 Maintain updated sectoral GiHA WG membership list, in coordination with SWG/SS Coordinators | Ongoing | Ongoing | GiHA Coordinator | Aug '24: GiHA WG membership list updated in Q1 via internal process - needs to be reviewed with SWG/SS Coordinators. |  |  | Responsibility of GiHA WG Coordinator, in collaboration with SWG/SS Coordinators & GiHA WG members. (Sector FPs must be able to participate in SWG/SS meetings).
1.3 | Result: Planning, impementation and monitoring of the JRP is informed by context specific, intersectional gender analyses. PT: Extent to which MEL mechanisms are gender-responsive. | 1.3.1 Refugee-related data collection, monitoring and reporting tools systematically incorporate, analyse & report on SADDD. | 1.3.1.1 Develop & disseminate guidance on gender sensitivity and SADD for RRR data collection efforts. | Ongoing | Ongoing | GiHA Coordinator, Gender Data TF | Jun '24: Guidance on gender data collection needs disseminated during cyclone in May. |  |  | To be assessed: Whether cyclone guidance should be updated (developed in 2018).
|  | 1.3.2 More than 50% of sector indicators are gender responsive. | 1.3.2.1 Review of JRP indicators & development of recommendations in support of gender analysis & SADD. | Q2 | TBC | UN Women (in chairing GiHA WG); GiHA WG members | Jul '24: Report developed on 2023 JRP indicators, with recommendations, & shared with ISCG.
|  |  | 1.3.2.2 Guidance on indicators (SADD and gender specific indicators) is dissemianted to the sectors via the Tipsheets (ref: 1.2.2.1) and by sectoral members of the GiHA WG. | Q3 | TBC | GiHA WG Sector FP members, with GiHA Coordinator support | Aug '24: Not yet initiated.
2. Local and national women-led, women's rights organizations participate meaningfully in the response
# | Gender equality results & performance tracking | Performance indicator | Actions | Timeframe |  | Responsible | Status |  |  | Remarks
|  |  |  | 2025 | 2026 |  |  | 25 | 26
2.1 | Result: Women-led, women's rights organizations (WLO-WROs) play a visible and active role in the response. PT: Extent to which humanitarian partners engage with and foster the leadership of national & local WLO-WROs and refugee women in coordination mechanisms. | 2.1.1 National/local WLO-WROs are represented on the GiHA WG. | 2.1.1.1 Consultation with national & local WLO, WROs to agree on GiHA WG TOR revisions. |  |  | GiHA Coordinator with UN Women | Sep'24 four WLO/WROs were elected though a consultation workshop
|  |  | 2.1.1.2 TWG on WLO/ WRO established and convening regularly, supporting WLO,WROs contributions to the GiHA and the RRR. | Q1-Q4 | Q1-Q4 | GiHA Coordinator with UN Women | Jan '25: Initiated. |  |  | To be led by local WL, WRO with support from UN Women & NGO Platform
|  | 2.1.2 JRP planning & RRR priorities are informed by the perspectives of local WLO-WROs and self-organised networks/groups of refugee women. | 2.1.2.1 Consultations conducted with local WLO-WROs to identify needs & priorities vis-à-vis the RRR & their role. | Q2 | Q2 | TWG-WL | (To be initiated in 2025).
|  |  | 2.1.2.2 Camp-level Consultations conducted with self-organised networks/groups of refugee women to identify needs, perspectives & priorities vis-à-vis the RRR & their role. | Q1 | TBC | GiHA Coordinator & GiHA WG | Feb'25 Conducted consultation at 20 camps
|  |  | 2.1.2.3 Camp-level consultations with self-organized groups of RR women to seek their perspectives. (This point is merged with the above point as the meaning is almost same) |  | TBC | TWG-WL | (To be initiated in 2025).
|  | 2.1.3 Crisis affected women's groups in the host community and self-organized refugee women's networks & groups are meaningfully engaged in the response. | 2.1.3.1 Mapping of self-organized networks/groups of RR women across the camps and Host Community |  | TBC | TWG-WL | (To be initiated in 2026). |  |  | Identified as a need in 2023.
|  |  | 2.1.3.2 Development of, and standardized training for self-organized networks/groups of RR women on leadership skills |  | TBC | TWG-WL | (To be initiated in 2026). |  |  | Identified as a need in 2023.
3. GiHA WG communication and advocacy increases awareness & visibility of gender equality issues in the RRR
# | Gender equality results & performance tracking | Performance indicator | Actions | Timeframe |  | Responsible | Status |  |  | Remarks
|  |  |  | 2025 | 2026 |  |  | 25 | 26
3.1 | Result: Joint communication & advocacy increase awareness among humanitarian actors on key gender equality commitments & frameworks PT: Common messages & joint events contribute to enhanced reach of joint communications/ campaigns on gender equality issues | 3.1.1: Increased awareness of IASC updated GE Policy among humanitarian actors | 3.1.1.1 Awareness raising sessions on IASC updated GE policy (GiHA WG; SWGs/SS) | Q1-Q4 | TBC | GiHA WG members: UN Women | Aug '24: Need identified to increase awareness.
|  |  | 3.1.1.2 Awareness raising sessions on IASC updated GE policy (camp management) | Q1-Q4 | Q1-Q2 | WL-TWG
|  | 3.1.2: Collaboration with ISCG coordination groups to campaign/promote critical gender equality issues. | 3.1.2.1 IWD event at RRRO, engaging all sectors/groups, WL-WROs, CiCs. | Q1 | Q1 | GiHA Coordinator, IWD TF |  |  |  | Close coordination with ISCG Communications WG.
|  |  | 3.1.2.2 Coordinated IWD events implemented in the camps with the leadership of WL/WROs, engaging all sectors and camp management. | Q1 | Q1 | GiHA Coordinator, IWD TF
|  |  | 3.1.2.3 Coordinated 16 DOA events implemented in the camps with the leadership of WL/WROs, engaging all sectors and camp management. | Q4 | Q4 | 16 DOA TF, led by GBV-SS with GiHA WG contributions
4. Organizational resources and capacities are in place to deliver on gender equality commitments
# | Gender equality results & performance tracking | Performance indicator | Actions | Timeframe |  | Responsible | Status |  |  | Remarks
|  |  |  | 2025 | 2026 |  |  | 24 | 25
4.1 | Result: FINANCIAL RESOURCES: PT: JRP funding appeals include minimum criteria for gender equality and empowerment of women & girls. | 4.1.1 Funding for GE is tracked through implementing the GAM as a requirement. | 4.1.1.1 Establishment & functioning of the GAM TF, including to ensure GAM TF members' participation in JRP Peer Review Teams. | Q3-Q4 | Q1 & TBC | GiHA Coordinator | initiated. |  |  | GiHA Coordinator to provide back-up support to the GAM TF.
|  |  | 4.1.1.2 Data collected for, and report developed on GAM review process. | Q1, Q4 | Q1, Q4 | GiHA Coordinator, GAM review TF | GAM review report drafted |  |  | GiHA WG - GAM Review Task Force; external specialist supported by UN Women
|  | 4.1.2 Sector/SS Coordinators and JRP appealing partners are aware of, and can identify key GAM requirements. | 4.1.1.1 GAM information package is updated & shared with SWGs/SSs. | Q3 | Q3 | GiHA Coordinator | Aug '24: GAM information package requires review & updating.
|  |  | 4.1.1.2 Townhall on new JRP includes GAM presentation | Q3/Q4 | Q3/Q4 | GiHA Coordinator
4.2 | Result: HUMAN RESOURCES: Adequate gender capacities and expertise is in place to ensure gender responsive programming and operations. PT: Required gender expertise is available to the Rohingya refugee response | 4.2.1 Capacity development on gender equality and gender mainstreaming is prioritized in the RRR. | 4.2.1.1 Develop & implement an updated GiHA WG Capacity Development Plan to build capacities on gender concepts & gender mainstreaming, SADD, GAM, etc. | Q3-Q4 |  | GiHA Coordinator & Sectoral GiHA WG focal points | To be initiated.
|  |  | 4.2.1.2 Identify and maintain an updated repository of existing capacity development tools useful within the context | Q3-Q4 |  | GiHA Coordinator & members | To be initiated.
|  |  | 4.2.1.3 Develop training for capacity development on gender sensitization & gender mainstreaming (PPT) for i) SWG/SS members ii) front-line camp-level actors, and facilitate trainings | Q4 | TBC | GiHA Coordinator & members | To be initiated.
|  |  | 4.2.1.4 Update and implement trainings on the GAM | Q3-Q4 | TBC | GiHA Coordinator & GAM TF | Aug '24: Existing materials need review & updating.
|  |  | 4.2.1.5 Coordinate additional support from the national GiHA WG for capacity building support on specific issues. |  |  |  | July '24: 15 CXB GiHA WG members learned skills in RGAs through 3-day training facilitated by nat GiHA WG in April '24 in Dhaka.
|  | 4.2.3 Progress is made toward gender parity in the humanitarian response. | 4.2.3.1. Assessment of gender parity issues across humanitarian organizations. |  |  |  | Aug '24: Rapid Assessment of GE in the Workplace report prepared in '23; final review pending for 2024.
|  |  | 4.2.3.4 Finalization and implementation of recommendations of Rapid Assessment. |  |  |  | Aug '24: Yet to be developed.
4.3 | Result: Gender equality and women’s empowerment is a regular topic of discussion in the ISCG, SWG/SS meetings. PT: The GiHA WG has clearly defined linkages with, and a reporting line to the ISCG and different sectors, ensuring coherent integration of GEWE within their planning documents and -processes. | 4.3.1 Capacity is in place to coordinate the GiHA WG. | 4.3.1.1 GiHA Coordinator is recruited and maintained. | 2024 | 2025 | UN Women | Jul '24: Completed.
|  |  | 4.3.1.2 Linkage between GiHA WG & Inter-Sector & ROCT meetings established through GiHA Coordinator participation in related meetings. |  |  | GiHA Coordinator | Jul '24: UN Women contributions to key meetings; GiHA Coordinator to assume this role as of Aug '24
|  |  | 4.3.1.3 Review TORs of SWG/SS & present recommendations on how to systematically improve integration of GE issues. |  |  | GiHA WG | Aug '24: Not yet initiated. |  |  | Integration of GE issues within work of SWGs/SSs identified as a priority by GiHA WG in 2023.
|  |  | 4.2.1.4 GiHA WG biannual work plan is planned and updated on an annual basis. |  |  | GiHA WG | Aug '24: WP based on May '23 consultation WS & inputs generated via GiHA WG meetings in '23--'24. Need to confirm consensus and seek final inputs. |  |  | Update on a rolling basis and via annual work planning WS.
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mehbuba Jabin - would be possible to update this
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: it is a regular work every year prior to JRP project proposals submission.