## planning
Draft WASH Sector Workplan 2025
Objectives / main activities | Lead | Importance | Timing
Develop long-term strategy and cost efficient of the WASH response
Operationalisation of the Water strategy | WASH co + Jafar | 4 | 1st Semester
Apply Rationzalisation principles | WASH Co, partners | 4 | Through the year
Renew SAG members | WASH Co, partners | 4 | 1st Semester
Integrate better climate change into WASH resilient program | WASH sector team | 3 | from March
Better integration of cost efficiency and sustainability in the operationsalisation of the response | WASH Co, partners, lead TCG | 4 | Through the year
Build capacities of partners
Organise regular webinars | Sector + partners | 3 | Through the year
Exchange of experience between actors at field level | Sector + partners + CFP | 4 | Through the year
Support key partners (new actors, camps with low performances) directly on the field, PF actors) | Sector + partners + CFP | 3 | Through the year
Training on emergency response | Sector + partner | 3 | first and second trimester
Organise WASH training on specific issues identified as gap (IM training, operation of water-network, chlorination…) | Sector team | 2 | Through the year
Reinforce prepardness and reponse capacity
Share early warning / alert | WASH sector, CFP | 3 | Through the year
Assess WASH items prepositionned for emergency response | IM | 3
Develop multi-sectorial plan for new influx | ISCG | 3
In collaboration with Health sector, review cholera response plan and threshold for JART deployment | WASH co, PHP, health sector | 3
Support needs evaluation | WASH co, liaison, Jafar
Develop a Concept note for Water response plan on fire (improving waternetworks) | Tehnical WASH, WASH co | 3
Collaborate with fire response agencies | WASH sector, CFP | 3
Strengh monitoring to identify priorities and gaps
Simplify 4W tool (one form for camps) | IM | 3 | From January
Promote 4W tool for HC / district | IM/UNICEF
Continue yearly implementation of 5 stars monitoring tool | MSF + jafar + tanvir | 3 | mid 2025
Kobo update on JART (following Cholera response plan) | tanvir + PHP |  | mid 2025
Develop HP/software monitoring tool | Tanvir/PHP/WASH co | 4 | 2nd semester 2025
Monitoring tools on corrective actions and recommendations | All | 3 | through the year
Two funding gaps analysis | IM/WASH co/ISCG | 4 | Feb and july 2025
Support ISNA or HH monitoring tool | AFA / IM / WASH Co/ISCG | 3 | 3rd trimester
Continue management and monitoring of key WASH sector IM tools | IM | 4 | through the year
Strenght collaboration with ISCG keys sectors
Report on JRP progress and develop JRP 2025 | WASH Co | 3 | through the year / last trimester
WASH's interests are represented within ISCG | WASH Co | 3 | through the year
Health - Outbreak preparedness and response (cholera + dengue) | PHP Specialist, MSF | 3 | 1st semester
SCCCM - collaboration integrated Shelter-WASH | WASH Co + jafar | 3 | through the year
Livelihood - collaboration on MHM & soap | WASH co, PHP | 3 | through the year
Develop ToR on WASH in institution | Sarita, WASH Co | 3 | 2nd trimester
Inclusion: Gender, resilience, environment, AAP | PHP Specialist | 3 | through the year
Strenght communication and partnership with authorities
Provide regular WASH updates to DPHE / RRRC | Liaison, WSH Co | 3 | through the year
Built-up working relationship with RRRC to support advocacy | Liaison, WSH Co | 4 | through the year
Increase collaboration with DPHE Dhaka and its partners (WB, ADB) | WASH Co / AFAs | 4 | through the year
Develop communication video/"pager" (MHM, Water) on achievements and challenges | WASH Co + Tonmoy | 3 | 1st semester 2024
Advocate to authorities on 1) Privatisation & policy; 2) …. | Liaison, WSH Co | 3 | 1st semester 2024
Advocate to main donors on gaps and priorities following "funding gaps analysis" | WASH Co + Tonmoy | 4 | February + July
Reinforce field coordination
Support WASH camps focal point system | Liaison | 4 | throught the year
Support partners at field level | Liaison | 4 | throught the year
Support Upuzila coordination (ISCG, host community and camps) | Liaison | 3 | throught the year
Focus on key technical issues / studies
Follow-up on MHM kits harmonisation | PHP lead + AFA | 4 | through the year
Strengh HP + CHW collaboration | PHP | 3
Study en dental hygiene (knowledge, pratice, dental kits…) | PHP | 3
harmonisation ToR on user group | PHP | 3
Assess impacts and solution for residual waste and recycling | WASH technical | 3
Child hygiene and well-being (study) | PHP | 3
WASH impact on AWD diseases | PHP + WASH Co | 3
Assess Waste generation at HH and shop level | WASH technical | 3
Study settled solid sludge | WASH technical | 3
Indoor bathing facilities | PHP | 3
Kolshi improvement for safer water storage/transport | PHP + UNICEF + NRC | 3